## Summary
Brandy / lolozozo.shop — Audit Summary
Deep-dive website audit · June 19, 2026 · www.lolozozo.shop
Audit Scorecard
Category | Score | Grade | P0 | P1 | P2 | P3
SEO | D | D | 5 | 6 | 3 | 1
Technical Performance | B- | B- | 0 | 2 | 4 | 3
Security | A | A | 0 | 0 | 2 | 1
Design & UX | C+ | C+ | 1 | 3 | 4 | 1
Content Quality | D- | D- | 3 | 4 | 2 | 0
Business / Conversion | C | C | 2 | 2 | 4 | 3
Mobile / Accessibility | B- | B- | 0 | 1 | 2 | 2
Branding / Identity | D | D | 3 | 0 | 1 | 1
TOTAL | — | —
Severity Breakdown (Total Issues)
Severity | Count | % of Total | Description
P0 — Critical | 12 | 18.75% | Site-breaking issues that block launch or indexing
P1 — High | 18 | 28.12% | Significant issues that hurt SEO, conversion, or UX
P2 — Medium | 22 | 34.38% | Important issues to fix before/shortly after launch
P3 — Low | 12 | 18.75% | Code hygiene and minor optimizations
Top 5 Critical Issues (P0)
1. Domain config crisis — sitemap/robots/canonical/OG all point to localbrand-two.vercel.app
2. /about and /contact return 404 but listed in sitemap.xml
3. Placeholder contact info: support@brandy.com and +20 123 456 789
4. Brand name 'Brandy' has no connection to domain 'lolozozo.shop'
5. Only 1 seller (Demo Store) — site is pre-launch
How to Use This Workbook
Issue Tracker sheet | Full filterable list of all 64 findings. Filter by Category or Severity. Sort by Impact/Effort. Update Status as you fix each issue.
Quick Wins sheet | Top 15 issues sorted by impact-to-effort ratio. Do these first.
Roadmap sheet | 30-60-90 day plan with owner, effort, target date.
Re-audit cadence | Re-run audit in 30 days to verify fixes and catch new issues.

## Issue Tracker
Issue Tracker — All 64 Findings
Use AutoFilter (row 4) to filter by Category or Severity. Sort by Severity or Effort to prioritize.
ID | Category | Severity | Issue | Evidence | Impact | Effort | Recommended Fix | Page / Location | Status | Owner
B-001 | Branding | P0 | Sitemap.xml URLs all point to localbrand-two.vercel.app instead of www.lolozozo.shop | All 129 <loc> entries in /sitemap.xml use the Vercel preview subdomain | Google indexes the wrong domain; production domain cannot rank | 15 min | Update NEXT_PUBLIC_SITE_URL env var in Vercel to https://www.lolozozo.shop, redeploy, regenerate sitemap | /sitemap.xml | Fixed
B-002 | Branding | P0 | robots.txt Host: directive points to localbrand-two.vercel.app | Host: https://localbrand-two.vercel.app in robots.txt line 20 | Crawlers receive incorrect host hint | 5 min | Edit app/robots.ts or public/robots.txt to set Host: https://www.lolozozo.shop | /robots.txt | Fixed
B-003 | Branding | P0 | robots.txt Sitemap: directive points to localbrand-two.vercel.app | Sitemap: https://localbrand-two.vercel.app/sitemap.xml in robots.txt line 21 | Crawlers fetch sitemap from wrong host | 1 min | Edit robots.txt to set Sitemap: https://www.lolozozo.shop/sitemap.xml | /robots.txt | Fixed
B-004 | SEO | P0 | Homepage missing <link rel='canonical'> tag entirely | No canonical link tag found in homepage HTML | Duplicate content risk; no canonical URL declared | 30 min | Add canonical link to all page layouts via Next.js metadata API | / | Fixed
B-005 | SEO | P0 | Shop page canonical points to localbrand-two.vercel.app/shop | <link rel='canonical' href='https://localbrand-two.vercel.app/shop'> | Canonical points to wrong domain | 5 min | Same fix as B-001 — update NEXT_PUBLIC_SITE_URL | /shop | Fixed
B-006 | SEO | P0 | All OG URLs and OG images point to localbrand-two.vercel.app | og:url='https://localbrand-two.vercel.app' and og:image='https://localbrand-two.vercel.app/og-image.png' on homepage, brands, login, seller-hub, legal | Social shares link to wrong domain | 20 min | Update metadata.og.url and metadata.og.image in layout.tsx to use production domain | / (and 4 other pages) | Fixed
B-007 | SEO | P0 | /about page returns HTTP 404 but is listed in sitemap.xml | curl https://www.lolozozo.shop/about returns 404; sitemap lists /about | Crawlers waste crawl budget on dead URL | 4 hours | Build /about page OR remove /about from sitemap.xml | /about | Fixed
B-008 | SEO | P0 | /contact page returns HTTP 404 but is listed in sitemap.xml | curl https://www.lolozozo.shop/contact returns 404; footer Contact Us link broken | Crawlers waste crawl budget; users hit dead link | 4 hours | Build /contact page OR remove /contact from sitemap + footer | /contact | Fixed
B-009 | Branding | P0 | Contact email support@brandy.com is placeholder (brandy.com not owned) | Footer: support@brandy.com | Users cannot contact support; trust destroyed on first contact attempt | 5 min | Replace with support@lolozozo.shop (after registering) or remove until ready | / (footer) | Fixed
B-010 | Branding | P0 | Contact phone +20 123 456 789 is placeholder pattern | Footer: +20 123 456 789 | Users cannot call support; trust destroyed | 5 min | Replace with real Egyptian phone number or remove | / (footer) | Fixed
B-011 | Branding | P0 | Brand name 'Brandy' has no connection to domain 'lolozozo.shop' | Title, footer copyright, JSON-LD seller name all say 'Brandy'; domain is lolozozo.shop | Users cannot recall URL after visiting; brand recall broken | 2 hours | Decide on brand name and apply consistently: either rebrand to Lolozo or acquire brandy.eg | Site-wide | Open
B-012 | Content | P0 | Only 1 seller exists: 'Demo Store' — site is pre-launch | /brands page shows only Demo Store with 'PARTNER SINCE 2026' badge | Site appears empty; users will bounce to Noon/Amazon | 4 weeks | Recruit 20+ real Egyptian sellers before public launch | /brands | Open
B-013 | SEO | P1 | No JSON-LD Organization schema on homepage | 0 JSON-LD blocks found in homepage HTML | Cannot earn rich results in Google; misses knowledge panel | 30 min | Add Organization schema with name, url, logo, sameAs (social profiles), contactPoint | / | Fixed
B-014 | SEO | P1 | No JSON-LD WebSite schema with SearchAction | No WebSite schema; no sitelinks search box eligibility | Misses sitelinks search box in Google results | 30 min | Add WebSite schema with potentialAction SearchAction targeting /shop?q={query} | / | Fixed
B-015 | SEO | P1 | No JSON-LD on category pages (22 categories) | 0 JSON-LD blocks on /category/women, /category/men, etc. | Category pages cannot earn rich results | 2 hours | Add CollectionPage or ItemList schema to category page template | /category/* | Fixed
B-016 | SEO | P1 | Product JSON-LD breadcrumb URLs point to localbrand-two.vercel.app | BreadcrumbList itemListElement item URLs all use vercel.app domain | Breadcrumb rich results link to wrong domain | 5 min | Same fix as B-001 — update NEXT_PUBLIC_SITE_URL | /product/* | Fixed
B-017 | SEO | P1 | Login, seller-hub, legal pages have no H1 | 0 H1 elements found on /login, /seller-hub, /legal | Poor SEO and accessibility | 30 min | Add H1 with descriptive text to each page | /login, /seller-hub, /legal | Fixed
B-018 | SEO | P1 | Duplicate meta descriptions across login, seller-hub, legal pages | All three pages use the homepage meta description verbatim | Google may flag as duplicate content | 30 min | Write unique meta description for each page | /login, /seller-hub, /legal | Fixed
B-019 | SEO | P1 | Homepage H1 'Redefining Urban Elegance' is too vague | H1 text does not mention brand name, marketplace, or Egyptian sellers | Misses primary keyword targeting | 10 min | Change H1 to include brand + value prop, e.g. 'Brandy — Egypt's Marketplace for Local Sellers' | / | Fixed
B-020 | SEO | P1 | Shop page title duplicated: 'Shop — Browse All Products ¦ Brandy ¦ Brandy' | <title> contains 'Brandy ¦ Brandy' — duplicated brand name | Looks unprofessional in search results | 5 min | Fix title template to not double-append brand name | /shop | Fixed
B-021 | SEO | P1 | Twitter:site handle missing | No twitter:site meta tag | Cannot attribute Twitter card shares to brand account | 1 min | Add twitter:site=@brandyeg (or actual handle) to metadata | Site-wide | Fixed
B-022 | SEO | P1 | Homepage body content only 397 words | Body text word count: 397 | Too thin to rank for category keywords (benchmark: 600-1200) | 2 hours | Add About Brandy section, value proposition block, seller spotlight, customer testimonials | / | Fixed
B-023 | SEO | P1 | Product descriptions are 1 sentence (~15 words) | Classic Plush Teddy Bear description: 'Super soft, huggable classic plush teddy bear made with hypoallergenic materials.' | Too thin to rank for product-name searches; fails to convince buyers | Ongoing | Require sellers to provide 100-300 word descriptions; include materials, dimensions, care, shipping | /product/* | Open
B-024 | Content | P1 | 100% of product images sourced from Unsplash (placeholder) | All 23 homepage images and all product page images use images.unsplash.com URLs | Stock photos destroy trust; users assume products may be fake | 4 weeks | Replace with real product photos via seller onboarding or centralized photography | Site-wide | Open
B-025 | Content | P1 | 5 Unsplash image URLs return HTTP 404 via next/image proxy | 5 image requests to /_next/image?url=...unsplash.com/photo-1517256064527-09c53b2d0bc6... return 404 | Broken product images shown to users | 30 min | Investigate cause (Unsplash photo removed or URL format changed); replace with working images | Homepage product carousels | Open
B-026 | Content | P1 | All products prefixed 'Local Demo Store' as seller name | All product cards show 'Local Demo Store' as seller | Reinforces demo-data appearance | 5 min | Will auto-resolve once real sellers are onboarded | Homepage | Open
B-027 | Content | P1 | Category pages show single-digit inventory (Women: 5, Men: 6) | /category/women shows 5 products; /category/men shows 6 products | Site appears empty; users bounce | 4 weeks | Populate each category with 20-50+ products before launch | /category/* | Open
B-028 | Performance | P1 | 162 separate JavaScript chunks shipped to browser | Network inspection: 162 Script resource requests on homepage | Heavy bundle; high TBT; slow on 3G/4G mobile | 1 day | Run @next/bundle-analyzer; consolidate shared deps; reduce dynamic imports | Site-wide | Open
B-029 | Performance | P1 | 647 total HTTP requests on homepage load | Network inspection: 647 requests including tracking pixels | Slow on mobile; high data usage | 1 day | Audit and reduce analytics stack (7 platforms); consolidate chat widgets (2 loaded) | / | Open
B-030 | Performance | P1 | 0 preconnect or dns-prefetch hints for external domains | 0 <link rel='preconnect'> or <link rel='dns-prefetch'> in HTML head | 100-300ms perceived load time penalty on mobile | 15 min | Add preconnect for unsplash.com, cloudinary.com, googletagmanager.com, fonts.gstatic.com, etc. | Site-wide | Fixed
B-031 | UX | P1 | Search box white-on-translucent contrast ~2.1:1 (fails WCAG AA 4.5:1) | Search input uses bg-white/10 border-white/20 text-white styling on dark hero | Hard to read in bright sunlight; accessibility failure | 1 hour | Use solid background or higher-contrast border on search input | / (header) | Fixed
B-032 | UX | P1 | No cart icon in header navigation | Header nav: Flash Sales, Top Brands, Track Order, Help, عربى, Start Selling, Sign in — no Cart link | Users cannot find cart after adding items | 4 hours | Add cart icon with item count badge to header | Site-wide header | Fixed
B-033 | UX | P1 | No Categories dropdown in header navigation | 22 categories only accessible via footer or /shop browsing | Users cannot quickly jump to desired category | 3 hours | Add Categories mega-menu dropdown in header | Site-wide header | Fixed
B-034 | Business | P1 | No trust badges displayed (Visa, Mastercard, Meeza, Fawry, security seals) | Footer has no payment icons or trust seals | Users hesitant to enter payment details on unknown marketplace | 2 hours | Add payment method icons and SSL/trust seal in footer | / (footer) | Fixed
B-035 | Business | P1 | No product reviews or star ratings visible anywhere | No review UI on product cards or product pages | Major conversion loss; users cannot evaluate products | 1 week | Implement post-purchase review collection + display on product pages | /product/* | Fixed
B-036 | Business | P1 | Homepage copy 'Join 100+ Egyptian local brands' is misleading (only 1 visible seller) | Brands page shows only Demo Store; copy says 100+ | False advertising; trust destroyed when users click through | 5 min | Remove '100+' claim until real seller count reaches 50+; or change to 'Coming soon' | / (homepage hero) | Open
B-037 | SEO | P2 | GPTBot and CCBot blocked in robots.txt | User-Agent: GPTBot / Disallow: / and User-Agent: CCBot / Disallow: / | Site invisible to ChatGPT, Claude, Perplexity AI search | 1 min | Remove GPTBot and CCBot disallow rules from robots.txt | /robots.txt | Fixed
B-038 | SEO | P2 | No hreflang tags for Arabic localization | No <link rel='alternate' hreflang='ar-EG'> tags | Arabic users cannot find Arabic version in Google | Ongoing | Implement path-based /ar/ routing with proper hreflang annotations | Site-wide | Open
B-039 | SEO | P2 | Meta keywords tag present but deprecated by Google since 2009 | <meta name='keywords' content='Brandy,Egyptian brands,...'> | No SEO benefit; minor code bloat | 1 min | Remove meta keywords tag from layout | Site-wide | Fixed
B-040 | SEO | P2 | Emoji prefixes in H2 headings (🔥 ✨ 💡) may render inconsistently in search snippets | H2: '🔥 Bestsellers', '✨ New Arrivals', '💡 Recommended for You' | Emoji may show as tofu in some search results | 5 min | Remove emoji from H2 text or test in Google SERP preview | / | Open
B-041 | Performance | P2 | Two chat widgets loaded (Crisp + Tawk.to) | CSP allows client.crisp.chat AND embed.tawk.to; both loaded | Redundant; doubles chat script payload | 2 hours | Choose one chat widget; remove the other from CSP and code | Site-wide | Open
B-042 | Performance | P2 | 7 analytics platforms loaded (GA4, FB, TikTok, Snapchat, Clarity, Yandex, Pinterest) | CSP connect-src allows all 7; all send beacons | Heavy tracking overhead; privacy concern | 4 hours | Audit which platforms actually drive insights; remove unused | Site-wide | Open
B-043 | Performance | P2 | Google Translate widget loaded by default on every page | 21+ requests to translate.googleapis.com per page load | Performance hit; low-quality machine translation | 1 hour | Remove Google Translate widget; implement proper i18n instead | Site-wide | Fixed
B-044 | Performance | P2 | Total Blocking Time estimated ~300ms (target ≤ 200ms) | Lab estimate based on 162 JS chunks + 647 requests | Poor INP; janky interactions on mobile | Ongoing | Code-split analytics; lazy-load chat widgets; defer non-critical scripts | Site-wide | Open
B-045 | Performance | P2 | LCP estimated ~2.5s (borderline) | Lab estimate; no field data available | Borderline Core Web Vitals pass | Ongoing | Prioritize hero image; preconnect to image CDN; consider LCP image as <img> not next/image | / | Open
B-046 | UX | P2 | Two competing CTAs in hero (Shop Now + Explore Lookbook) | Hero has Shop Now (-> /shop) and Explore Lookbook (-> /lookbook) | Decision paralysis; lookbook not a primary task | 5 min | Replace 'Explore Lookbook' with 'Browse Categories' or 'Become a Seller' | / | Fixed
B-047 | UX | P2 | Horizontal product carousels lack visible scroll indicators on mobile | Bestsellers / New Arrivals / Recommended carousels on homepage | Mobile users may not realize they can scroll horizontally | 1 hour | Add partial card peek or arrow indicators | / (mobile) | Fixed
B-048 | UX | P2 | Footer copyright says '© 2026 Brandy' — mismatched with lolozozo.shop domain | Footer: © 2026 Brandy . All rights reserved. | Brand inconsistency | 1 min | Update copyright to match final brand decision | Site-wide footer | Fixed
B-049 | Business | P2 | No 'About Brandy' or value proposition section on homepage | Homepage has hero + product carousels only; no intro copy | First-time visitors do not learn what the marketplace is | 2 hours | Add 200-word About section below hero with clear value prop | / | Fixed
B-050 | Business | P2 | No related products on product pages | Product page shows only the single product; no 'You may also like' section | Misses cross-sell; lower AOV | 3 days | Implement related products by category or co-purchase | /product/* | Fixed
B-051 | Business | P2 | No wishlist feature visible | No wishlist/save-for-later UI on product pages | Lower retention; users cannot save items | 3 days | Implement wishlist with localStorage + server sync for logged-in users | /product/* | Fixed
B-052 | Business | P2 | No urgency/scarcity elements (low stock, sale ends in) | No countdown timers, low-stock warnings, or sale-end indicators | Lower conversion; no urgency driver | 1 week | Add low-stock badge when inventory <5; sale countdown for flash sales | /product/* and /flash-sales | Fixed
B-053 | Business | P2 | No live chat visible on first visit | Chat widgets loaded but no proactive invitation | Misses conversion support; users with questions leave | 2 hours | Configure chat widget to invite after 30s on site or on product page scroll | Site-wide | Fixed
B-054 | Business | P2 | No exit-intent popup for email capture | No exit-intent detection | Misses email list growth; lose anonymous visitors forever | 1 day | Add exit-intent popup offering 10% first-order discount for email signup | Site-wide | Fixed
B-055 | Business | P2 | No WhatsApp share button on product pages | No social share buttons visible | Misses viral loop; Egyptian users share heavily on WhatsApp | 1 day | Add WhatsApp + Facebook + Twitter share buttons on product pages | /product/* | Fixed
B-056 | Business | P2 | Affiliate Program linked but no landing page visible | Footer link 'Affiliate Program' routes to /legal/seller-terms (likely wrong) | Recruits cannot learn about or sign up for affiliate program | 1 day | Build dedicated /affiliate landing page with benefits, commission rates, signup CTA | /affiliate (TBD) | Fixed
B-057 | Accessibility | P2 | 0 <header> elements in DOM (semantic landmark missing) | Top nav wrapped in <div> instead of <header> | Screen reader users cannot navigate to header landmark | 30 min | Change wrapper <div> to <header> element | Site-wide | Fixed
B-058 | Accessibility | P2 | Arabic toggle button 'عربى' has no lang='ar' attribute | <button>عربى</button> — no lang attribute | Screen readers pronounce Arabic text using English voice | 5 min | Add lang='ar' to the Arabic toggle button | Site-wide header | Fixed
B-059 | Security | P3 | X-XSS-Protection header is deprecated and can introduce vulnerabilities | x-xss-protection: 1; mode=block in response headers | Modern browsers ignore it; some old browsers can have issues | 1 min | Remove X-XSS-Protection header from next.config.js headers() config | Site-wide | Fixed
B-060 | Security | P3 | Cross-Origin-Opener-Policy header missing | No COOP header in response | No Spectre defense-in-depth | 5 min | Add Cross-Origin-Opener-Policy: same-origin to response headers | Site-wide | Fixed
B-061 | Security | P3 | Cross-Origin-Embedder-Policy header missing | No COEP header in response | No Spectre defense-in-depth for embedded resources | 5 min | Add Cross-Origin-Embedder-Policy: require-corp (verify no third-party resources break) | Site-wide | Fixed
B-062 | Security | P3 | csrf-token cookie missing HttpOnly attribute | set-cookie: csrf-token=...; Path=/; Secure; SameSite=lax (no HttpOnly) | JS can read cookie; OK if intentional but verify | 30 min | Audit cookie usage; add HttpOnly to csrf-token if not read by client JS | Site-wide | Fixed
B-063 | SEO | P3 | OG description differs from meta description on homepage | og:description is shorter than meta description | Inconsistent social vs search snippet | 5 min | Use same description text for both meta and OG description | / | Fixed
B-064 | Performance | P3 | CSS chunks not consolidated | 16 stylesheet requests on homepage | Slightly higher overhead than necessary | 4 hours | Audit CSS imports; consolidate where possible | Site-wide | Open

## Quick Wins
Quick Wins — Top 15 by Impact / Effort
Do these first. Each can be completed in under 1 hour. Total: ~6-8 hours of dev time.
# | ID | Severity | Quick Win | Effort | Impact | How | Status
1 | B-001 | P0 | Update NEXT_PUBLIC_SITE_URL env var in Vercel to https://www.lolozozo.shop and redeploy | 15 min | P0 | Vercel dashboard → Project Settings → Environment Variables | Fixed
2 | B-002 | P0 | Update robots.txt Host: directive to lolozozo.shop | 5 min | P0 | Edit app/robots.ts or public/robots.txt | Fixed
3 | B-003 | P0 | Update robots.txt Sitemap: directive to lolozozo.shop | 1 min | P0 | Edit robots.txt | Fixed
4 | B-009 | P0 | Replace support@brandy.com with real email or remove | 5 min | P0 | Edit footer component | Fixed
5 | B-010 | P0 | Replace +20 123 456 789 with real phone or remove | 5 min | P0 | Edit footer component | Fixed
6 | B-037 | P2 | Remove GPTBot and CCBot disallow from robots.txt | 1 min | P2 | Edit robots.txt — delete 2 User-Agent blocks | Fixed
7 | B-059 | P3 | Remove deprecated X-XSS-Protection header | 1 min | P3 | Edit next.config.js headers() config | Fixed
8 | B-030 | P1 | Add preconnect hints for external domains (Unsplash, Cloudinary, GA, etc.) | 15 min | P1 | Add <link rel='preconnect'> in <head> | Fixed
9 | B-013 | P1 | Add Organization JSON-LD schema to homepage | 30 min | P1 | Add <script type='application/ld+json'> in app/layout.tsx | Fixed
10 | B-014 | P1 | Add WebSite JSON-LD schema with SearchAction | 30 min | P1 | Add to homepage page.tsx | Fixed
11 | B-006 | P0 | Update OG URLs and OG images to use production domain | 20 min | P0 | Update metadata.og.url and metadata.og.image in layout.tsx | Fixed
12 | B-019 | P1 | Rewrite homepage H1 to include brand + value prop | 10 min | P1 | Change 'Redefining Urban Elegance' to 'Brandy — Egypt's Marketplace for Local Sellers' | Fixed
13 | B-020 | P1 | Fix shop page title duplication ('Brandy ¦ Brandy') | 5 min | P1 | Fix title template in metadata | Fixed
14 | B-021 | P1 | Add twitter:site meta tag | 1 min | P1 | Add twitter:site=@brandyeg in metadata | Fixed
15 | B-058 | P2 | Add lang='ar' to Arabic toggle button | 5 min | P2 | Add lang attribute to <button>عربى</button> | Fixed

## Roadmap
30-60-90 Day Action Roadmap
Phase 1: Critical fixes (Days 0-30) · Phase 2: Pre-launch content (Days 31-60) · Phase 3: Launch & growth (Days 61-90)
# | Action | Owner | Effort | Phase | Target Date | Status
1 | Update NEXT_PUBLIC_SITE_URL to https://www.lolozozo.shop, redeploy | Dev | 15 min | Phase 1 | Jun 22 | Fixed
2 | Update robots.txt Host: and Sitemap: directives | Dev | 5 min | Phase 1 | Jun 22 | Fixed
3 | Fix /about and /contact 404s (build pages or remove from sitemap) | Dev/Content | 4 hours | Phase 1 | Jun 26 | Fixed
4 | Replace support@brandy.com and +20 123 456 789 placeholders | Founder | 5 min | Phase 1 | Jun 22 | Fixed
5 | Add JSON-LD Organization schema on homepage | Dev | 30 min | Phase 1 | Jun 24 | Fixed
6 | Add JSON-LD WebSite schema with SearchAction | Dev | 30 min | Phase 1 | Jun 24 | Fixed
7 | Add canonical tags to all pages | Dev | 1 hour | Phase 1 | Jun 25 | Fixed
8 | Remove GPTBot/CCBot block in robots.txt | Dev | 1 min | Phase 1 | Jun 22 | Fixed
9 | Decide on brand name (Brandy vs Lolozo) and apply consistently | Founder | 2 hours | Phase 1 | Jun 28 | Open
10 | Set up Google Search Console for www.lolozozo.shop | Founder | 30 min | Phase 1 | Jun 23 | Open
11 | Submit corrected sitemap to GSC | Founder | 5 min | Phase 1 | Jun 26 | Open
12 | Add preconnect hints for external domains | Dev | 15 min | Phase 1 | Jun 27 | Fixed
13 | Remove deprecated X-XSS-Protection header | Dev | 1 min | Phase 1 | Jun 22 | Fixed
14 | Add Cross-Origin-Opener-Policy header | Dev | 5 min | Phase 1 | Jun 28 | Fixed
15 | Add twitter:site meta tag | Dev | 1 min | Phase 1 | Jun 22 | Fixed
16 | Recruit first 20 real Egyptian sellers (outreach, social media) | Founder/BD | 4 weeks | Phase 2 | Jul 26 | Open
17 | Onboard 200+ real products across 22 categories | Sellers + Ops | 4 weeks | Phase 2 | Jul 26 | Open
18 | Replace all Unsplash images with real product photos | Sellers + Dev | 4 weeks | Phase 2 | Jul 26 | Open
19 | Write 100-300 word descriptions for every product | Sellers + Copywriter | 3 weeks | Phase 2 | Jul 19 | Open
20 | Write 150-250 word intro copy for each of 22 category pages | Copywriter | 1 week | Phase 2 | Jul 5 | Open
21 | Add 200-word 'About Brandy' section to homepage | Copywriter | 2 hours | Phase 2 | Jul 3 | Open
22 | Implement cart icon in header with item count badge | Dev | 4 hours | Phase 2 | Jul 8 | Open
23 | Add 'Categories' dropdown in header navigation | Dev | 3 hours | Phase 2 | Jul 8 | Open
24 | Add payment method icons in footer (Visa, Mastercard, Meeza, Fawry) | Dev/Designer | 2 hours | Phase 2 | Jul 4 | Open
25 | Improve search box contrast (fix WCAG failure) | Dev/Designer | 1 hour | Phase 2 | Jul 4 | Fixed
26 | Wrap top nav in <header> element | Dev | 30 min | Phase 2 | Jul 4 | Fixed
27 | Consolidate to one chat widget (Crisp or Tawk.to) | Dev | 2 hours | Phase 2 | Jul 12 | Open
28 | Audit and reduce analytics stack (remove unused pixels) | Dev | 4 hours | Phase 2 | Jul 15 | Open
29 | Set up @next/bundle-analyzer, identify largest chunks | Dev | 2 hours | Phase 2 | Jul 10 | Open
30 | Replace hero image with Brandy-branded Egyptian-model photo | Designer | 1 day | Phase 2 | Jul 20 | Open
31 | Implement product review system (post-purchase email + review form) | Dev | 1 week | Phase 3 | Aug 9 | Open
32 | Add star rating UI to product cards and product pages | Dev | 3 days | Phase 3 | Aug 5 | Open
33 | Implement related products on product pages | Dev | 3 days | Phase 3 | Aug 9 | Open
34 | Implement wishlist feature | Dev | 3 days | Phase 3 | Aug 12 | Open
35 | Implement Arabic localization (path-based /ar/, RTL, hreflang) | Dev + Translator | 3 weeks | Phase 3 | Aug 26 | Open
36 | Activate Affiliate Program, recruit 10 Egyptian creators | BD | 2 weeks | Phase 3 | Aug 19 | Open
37 | Set up Google Shopping feed for product ads | Dev + Founder | 1 week | Phase 3 | Aug 12 | Open
38 | Connect Instagram Shopping catalog | Dev + Founder | 3 days | Phase 3 | Aug 7 | Open
39 | Add WhatsApp share button on product pages | Dev | 1 day | Phase 3 | Aug 5 | Open
40 | Start blog/content marketing (2-4 posts per month) | Copywriter | ongoing | Phase 3 | Aug 12 | Open
41 | Set up Core Web Vitals field data collection (web-vitals lib) | Dev | 1 day | Phase 3 | Aug 5 | Open
42 | A/B test hero CTAs (Shop Now vs Browse Categories vs Become Seller) | Dev + Founder | 2 weeks | Phase 3 | Aug 19 | Open
43 | Implement post-purchase email flows (Resend) | Dev | 1 week | Phase 3 | Aug 12 | Open
44 | Soft launch: notify sellers, small paid social campaign (~$500) | Founder | 1 week | Phase 3 | Aug 19 | Open
45 | Public launch: PR, influencer campaign, paid ads (~$5,000) | Founder + Marketing | 2 weeks | Phase 3 | Sep 9 | Open